## Data
Name | Work Product | Iteration | Tags | Scheduled State | Estimate | To Do | Actuals | Owner | Project | Estimation variance ((act+todo)/estimated) | non empty
QE - Promotion to SYS environment | US379380: [leftovers] GetGroupConversionInfo Service Migration | Sprint 18.1.4 | "tt:deploy" | Defined | 6 | 6 |  | Anton Guba | The Hussars | 1 | y
QE - Update test statuses in ALM | US379380: [leftovers] GetGroupConversionInfo Service Migration | Sprint 18.1.4 | "tt:alm" | Completed | 2 | 0 | 2 | Illia Zaitsev | The Hussars | 1 | y
DEV - Deploy the artifact into DEV environment | US379380: [leftovers] GetGroupConversionInfo Service Migration | Sprint 18.1.4 | "tt:deploy" | Completed | 10 | 0 | 16 | Jafar Qaddoumi | The Hussars | 1.6 | y
Provision and configure several CPC JBoss Fuse instances for dev purposes | US383050: CPC/Fuse deployment automation | Sprint 18.1.4 | "tt:deploy" | Completed | 16 | 0 | 17 | Barys Hainulin | The Hussars | 1.0625 | y
Deployment to CPC automation. | US383050: CPC/Fuse deployment automation | Sprint 18.1.4 | "tt:env" | Completed | 16 | 0 | 15 | Barys Hainulin | The Hussars | 0.9375 | y
CXF transport component for camel | US379380: [leftovers] GetGroupConversionInfo Service Migration | Sprint 18.1.4 | "tt:code" | Defined | 20 | 19 | 1 | Barys Hainulin | The Hussars | 1 | y
QA-add L7 credentials | US379380: [leftovers] GetGroupConversionInfo Service Migration | Sprint 18.1.4 | "tt:qe-framework" | Completed | 4 | 0 | 4 | Anton Guba | The Hussars | 1 | y
QE-Create test cases in ALM | US383047: Get Accumulation Automation | Sprint 18.1.4 | "tt:alm" | Completed | 12 | 0 | 12 | Anton Guba | The Hussars | 1 | y
QE-Test Cases Automation | US383047: Get Accumulation Automation | Sprint 18.1.4 | "tt:qe-automation" | In-Progress | 20 | 8 | 26 | Illia Zaitsev | The Hussars | 1.7 | y
QE-SoapUI project creation | US383047: Get Accumulation Automation | Sprint 18.1.4 | "tt:qe-manual" | Completed | 10 | 0 | 12 | Illia Zaitsev | The Hussars | 1.2 | y
QE-Data preparation | US383047: Get Accumulation Automation | Sprint 18.1.4 | "tt:qe-manual" | Completed | 6 | 0 | 6 | Anton Guba | The Hussars | 1 | y
QE-Execution and Reporting | US383047: Get Accumulation Automation | Sprint 18.1.4 | "tt:qe-automation" | Completed | 4 | 0 | 8 | Anton Guba | The Hussars | 2 | y
QE-call GetMembers mock | US383048: Integration to GetMember | Sprint 18.1.4 | "tt:qe-framework" | Defined | 4 | 4 |  | Anton Guba | The Hussars | 1 | y
DEV - Camel Route | US383045: GetAccumulation Service Migration | Sprint 18.1.4 | "tt:code" | Completed | 16 | 0 | 19 | Marcin Bulawa | The Hussars | 1.1875 | y
DEV - Route Exception Handlers | US383045: GetAccumulation Service Migration | Sprint 18.1.4 | "tt:code" | Completed | 24 | 0 | 30 | Pawel Labaj | The Hussars | 1.25 | y
DEV - Marshalling and unmarshalling Processors | US383045: GetAccumulation Service Migration | Sprint 18.1.4 | "tt:code" | Completed | 24 | 0 | 32 | Marcin Bulawa | The Hussars | 1.3333 | y
DEV - Get data from DB | US383045: GetAccumulation Service Migration | Sprint 18.1.4 | "tt:deploy" | Completed | 16 | 0 | 14 | Mateusz Finek | The Hussars | 0.875 | y
DEV - Get data from External Service | US383048: Integration to GetMember | Sprint 18.1.4 | "tt:code" | In-Progress | 32 | 3 | 24 | Mateusz Finek | The Hussars | 0.84375 | y
DEV - Logging & Velocity templates | US383045: GetAccumulation Service Migration | Sprint 18.1.4 | "tt:code" | Completed | 12 | 0 | 16 | Pawel Labaj | The Hussars | 1.3333 | y
DEV - Spike/POC mocking myBatis data source | US383048: Integration to GetMember | Sprint 18.1.4 | "tt:investigate" | Defined | 4 | 4 |  | Pawel Labaj | The Hussars | 1 | y
Rename the GetGroupConversion service to GetGroupConversionInfo | US379380: [leftovers] GetGroupConversionInfo Service Migration | Sprint 18.1.4 | "tt:env" | Completed | 6 | 0 | 6 | Barys Hainulin | The Hussars | 1 | y
QE - Test case/scenario Creation | US379511: Test Cases Preparation and Review | Sprint 18.1.3 | "tt:qe-manual" | Completed | 6 | 0 | 6 | Anton Guba | The Hussars | 1 | y
QE - SoapUI project creation | US379511: Test Cases Preparation and Review | Sprint 18.1.3 | "tt:qe-manual" | Completed | 4 | 0 | 4 | Illia Zaitsev | The Hussars | 1 | y
QE - Promotion to SYS environment | US379511: Test Cases Preparation and Review | Sprint 18.1.3 | "tt:deploy" | Defined | 6 | 6 |  | Anton Guba | The Hussars | 1 | y
QE - Update test statuses in ALM | US379511: Test Cases Preparation and Review | Sprint 18.1.3 | "tt:alm" | In-Progress | 2 | 2 |  | Illia Zaitsev | The Hussars | 1 | y
DEV - Create Camel routing with AMQ | US379380: GetGroupConversionInfo Service Migration | Sprint 18.1.3 | "tt:code" | In-Progress | 15 | 2 | 15 | Marcin Bulawa | The Hussars | 1.1333 | y
DEV - (un)marshalling Request & Response | US379380: GetGroupConversionInfo Service Migration | Sprint 18.1.3 | "tt:code" | Completed | 8 | 0 | 14 | Mateusz Finek | The Hussars | 1.75 | y
DEV - DB Call handling | US379380: GetGroupConversionInfo Service Migration | Sprint 18.1.3 | "tt:code" | Completed | 12 | 0 | 17 | Jafar Qaddoumi | The Hussars | 1.4167 | y
DEV - Logging (Splunk, MDC, Log4j) | US379380: GetGroupConversionInfo Service Migration | Sprint 18.1.3 | "tt:code" | In-Progress | 10 | 0.5 | 2 | Mateusz Finek | The Hussars | 0.25 | y
DEV - Setting up security, SLA & reports | US379380: GetGroupConversionInfo Service Migration | Sprint 18.1.3 | "tt:investigate" | Defined | 10 | 1 | 1 | Mateusz Finek | The Hussars | 0.2 | y
QE - Setup Maven project | US379322: GetGroupConversionInfo Test Automation | Sprint 18.1.3 | "tt:ci" | Completed | 3 | 0 | 3 | Illia Zaitsev | The Hussars | 1 | y
QE - Develop Automation Framework Utils for SOAP requests/responses | US379322: GetGroupConversionInfo Test Automation | Sprint 18.1.3 | "tt:qe-framework" | Completed | 8 | 0 | 12 | Anton Guba | The Hussars | 1.5 | y
QE - Data preparation | US379322: GetGroupConversionInfo Test Automation | Sprint 18.1.3 | "tt:qe-manual" | Completed | 4 | 0 | 4 | Illia Zaitsev | The Hussars | 1 | y
QE - Test Report Creation | US379322: GetGroupConversionInfo Test Automation | Sprint 18.1.3 | "tt:qe-manual" | Completed | 8 | 0 | 22 | Anton Guba | The Hussars | 2.75 | y
DEV - Create stub project in git repo | US379317: Stub project creation | Sprint 18.1.3 | "tt:code" | Completed | 4 | 0 | 4 | Marcin Bulawa | The Hussars | 1 | y
DEV - Setup Jenkins build pipeline for DEV | US379484: Continuous Delivery Setup | Sprint 18.1.3 | "tt:ci" | Completed | 6 | 0 | 4 | Jafar Qaddoumi | The Hussars | 0.66667 | y
DEV - SonarQube setup request | US379484: Continuous Delivery Setup | Sprint 18.1.3 | "tt:ci" | Completed | 8 | 0 | 5 | Jafar Qaddoumi | The Hussars | 0.625 | y
DEV - Create the fabric profiles | US379484: Continuous Delivery Setup | Sprint 18.1.3 | "tt:env" | In-Progress | 6 | 0 | 46 | Barys Hainulin | The Hussars | 7.6667 | y
DEV - Deploy the artifact into DEV environment | US379484: Continuous Delivery Setup | Sprint 18.1.3 | "tt:deploy" | In-Progress | 10 | 10 |  | Jafar Qaddoumi | The Hussars | 1 | y
QE - Manage different environment in Automation | US379322: GetGroupConversionInfo Test Automation | Sprint 18.1.3 | "tt:env" | Completed | 5 | 0 | 5 | Anton Guba | The Hussars | 1 | y
DEV - Deployment procedure investigation and documentation | US379484: Continuous Delivery Setup | Sprint 18.1.3 | "tt:investigate" | Completed | 10 | 0 | 6 | Barys Hainulin | The Hussars | 0.6 | y
Connect framework with CPC environment | US379322: GetGroupConversionInfo Test Automation | Sprint 18.1.3 | "tt:env" | Defined | 4 | 4 |  | Barys Hainulin | The Hussars | 1 | y
QE - Automate Test Case TC_01_GetGroupConversionService_ValidData | US379322: GetGroupConversionInfo Test Automation | Sprint 18.1.3 | "tt:qe-automation" | Completed | 3 | 0 | 3 | Anton Guba | The Hussars | 1 | y
QE - Automate Test Case TC_02_GetGroupConversionService_ValidData_NonExistingGroupId | US379322: GetGroupConversionInfo Test Automation | Sprint 18.1.3 | "tt:qe-automation" | Completed | 3 | 0 | 4 | Illia Zaitsev | The Hussars | 1.3333 | y
QE - Automate Test Case TC_03_GetGroupConversionService_ValidData_EmptyGroupId | US379322: GetGroupConversionInfo Test Automation | Sprint 18.1.3 | "tt:qe-automation" | Completed | 3 | 0 | 4 | Illia Zaitsev | The Hussars | 1.3333 | y
QE - Automate Test Case TC_04_GetGroupConversionService_InvalidData | US379322: GetGroupConversionInfo Test Automation | Sprint 18.1.3 | "tt:qe-automation" | Completed | 3 | 0 | 4 | Illia Zaitsev | The Hussars | 1.3333 | y
QE - Automate Test Case TC_05_GetGroupConversionService_InvalidLength | US379322: GetGroupConversionInfo Test Automation | Sprint 18.1.3 | "tt:qe-automation" | Completed | 3 | 0 | 3 | Anton Guba | The Hussars | 1 | y
Create a bundle that expose endpoints | US386284: [POC] Mocking of test Environment | Sprint 18.1.3 | "tt:investigate" | In-Progress | 12 | 4 | 18 | Jafar Qaddoumi | The Hussars | 1.8333 | y
DEV - Apply Sonar rules | US379380: GetGroupConversionInfo Service Migration | Sprint 18.1.3 | "tt:code" | Completed | 5 | 0 | 5 | Pawel Labaj | The Hussars | 1 | y
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n
[10 empty] | #DIV/0! | n